MSc Dissertation Project Monthly  Attendance and Progress Report

TO BE COMPLETED BY THE STUDENT, WITH COMMENTS FROM THE SUPERVISOR.

Please complete all sections below

| Name | Arka Talukder | Student ID | B01821011 |
| --- | --- | --- | --- |
| Supervisor | Dr. Raja Ujjan | Start Date | 29/01/2026 |
| Mode of Study | Online | Dates of Meetings (include dates of all meetings) | 06/02/2026 (Online) 13/02/2026 (Online) 10/02/2026 (Online) – Title selection 11/02/2026 (Online) – Title approval 20/02/2026 (Online) 06/03/2026 (Online) |

| Description of Meetings | During this reporting period, I held regular supervisory meetings with Sir Dr. Raja Ujjan to discuss my dissertation project on Explainable dynamic graph neural network SIEM for Software-Defined IoT. In the first meetings (6 February), we discussed the project scope and what the interim report should include. On 10 and 11 February, the project title was selected and approved by the supervisor. After that, we focused on the project specification. This includes four main parts: dynamic GNN, federated learning, explainability, and SIEM integration. Later meetings covered the literature review structure, research gap, and methodology design. The supervisor gave feedback on graph construction, model choices, and evaluation metrics. We also discussed how to structure the interim report and present the work clearly. Recent meetings reviewed my implementation progress and the interim report draft. I presented the data pipeline, all four models (Random Forest, MLP, centralised GNN, federated GNN), explainability module, and SIEM API. The interim report is about 80% complete. I will seek final approval from the supervisor in the next week. |
| --- | --- |

Summary of work undertaken this month.

During this month, I completed most of the work needed for the interim report. Key achievements include: • Project title approved (10–11 February 2026) • Literature review written, covering IoT security, SDIoT, ML for intrusion detection, GNNs, federated learning, and explainable AI • Research gap table completed, comparing my project with related work • Methodology section written: dataset (CICIoT2023), preprocessing, graph construction, model architectures, evaluation metrics • Data pipeline implemented: CICIoT2023 loaded, preprocessed, normalised, exported as Parquet • Graph construction implemented: kNN builder, windowing, sequence dataset • All four models implemented: Random Forest, MLP, centralised dynamic GNN (GAT+GRU), federated GNN • Federated learning setup: Flower framework, non-IID data splitting, 10-round simulation • Explainability: Integrated Gradients (Captum) and GAT attention weights • SIEM integration: FastAPI endpoint producing ECS-formatted JSON alerts • Plan for completion section written with timeline and contingency plans • Interim report draft completed (approximately 80%); awaiting supervisor approval.

What work will you undertake next month?

In the upcoming period, I will focus on: • Obtaining supervisor approval for the interim report • Finalising any edits based on supervisor feedback • Completing final experiments and generating all figures (confusion matrices, ROC curves, FL convergence) • Writing the Results and Discussion chapters for the final dissertation • Conducting sensitivity analysis if time permits • Writing Conclusion and Critical Reflection • Final proofreading and submission I remain on schedule for timely completion.

Please detail reasons for any absence including the total number of days absent (annual leave, conference attendance, field research, ill health etc)?

I missed 27/02/2026 meeting due to GP appointment

Statement from Supervisor (including any issues which should be brought to the attention of School, indication of satisfactory process thus far and whether or not attendance has been satisfactory)

| Signed (student) |  | Date | 12/03/2026 |
| --- | --- | --- | --- |
| Signed (MSc Dissertation Supervisor) |  | Date |  |